Smart Parking System

## 1. Problem Statement

Employees at the new tech park spend up to 30 minutes searching for a parking spot due to lack of real-time guidance.

This causes:

- High frustration and stress

- Lost productivity

- Congestion at entry and exit points

SMART OBJECTIVE:

Objective: Reduce parking search time

- Specific: Guide employees to spots

- Measurable: Avg search ≤ 5 min

- Achievable: Use cameras/software

- Relevant: Reduces frustration

- Time-bound: 2 weeks

## 2. Scope Statement

Included:

- Use existing security cameras to see which spots are empty or full.

- Software to track spots in real time.

- Mobile app or web page to show available spots.

- Collect basic parking data (usage trends).

- Optional: show info on digital signs.

Excluded:

- Buying new sensors (ground sensors, LIDAR, etc.)

- Advanced AI that low-res cameras cannot handle

- Reserving specific spots for users

## 3.Technical Feasibility

- The cameras we already have can see if a car is there.

- We can run the software on a normal computer.

- Free tools (like OpenCV) can help detect cars.

OpenCV means Open Source Computer Vision.

- It’s free software that helps computers “see” things in pictures or videos.

- It can detect cars, people, or motion.

- For our project, it tells if a parking spot is full or empty

- Problem: if the camera doesn’t see a spot, we won’t know if it’s empty.

COST Feasibility

   $ 2,500 → pay the people who make the software

   $ 500 → buy computer or cloud server

   $ 1,000 → make app or website

   $500 (optional) → buy screen or display

   $500 → extra money for surprises

## 4. Work Breakdown Structure

Day 1–2: Planning

- Decide which parking zones to watch.

- Check where cameras are and what they can see.

- Make a simple map of the parking lot.

Day 3–10: Software

- Make software to detect cars and empty spots.

- Build dashboard to show free spots in real time.

- Connect cameras so the system gets video.

Day 11–12: Testing

- Check if car detection is working.

- Test during busy parking times.

- Fix any mistakes in detection.

Day 13: Deployment

- Put dashboard on PC or server.

- Make sure everything works correctly.

Day 14: Training

- Show staff and managers how to use system.

- Give simple instructions to maintain it.

5. Initial Risk Register